## Tasksheet
No | Member | Contents |  | Table Name | Activity Plan | Date of Preparation of Activity Plan
[5 empty] | Planed Start Date | Actual Start Date | Actual Days | Status
1 | Lê Viết Đông | Admin | Schedule management Page(View,New, Edit, Delete Scheule) | Ticket, Schedule, ProductBill | 2023-03-21 | 2023-03-25 | 5 | OK
|  |  | Report for Product and export to Excel |  | 2023-03-28 | 2023-04-01 | 5 | OK
|  | User | Ticket Page |  | 2023-04-04 | 2023-04-08 | 5 | OK
|  |  | Product Page |  | 2023-04-11 | 2023-04-25 | 5 | OK
2 | Huỳnh Tấn Phước | Admin | Employee managerment Page (View,New, Edit, Delete Employee) | Employee, WorkSession | 2023-03-21 | 2023-03-25 | 5 | OK
|  |  | Login Page |  | 2023-03-28 | 2023-04-01 | 5 | OK
|  |  | Report for Employee and export to Excel |  | 2023-04-04 | 2023-04-08 | 5 | OK
|  | User | Change information and password |  | 2023-04-11 | 2023-04-25 | 5 | OK
3 | Nguyễn Nhật Minh | Admin | Customer managerment Page (View,New, Edit Customer) | Customer, Bill | 2023-03-21 | 2023-03-25 | 5 | OK
[5 empty] | 2023-03-28 | 2023-04-01 | 5 | OK
|  |  | Export Bill |  | 2023-04-04 | 2023-04-08 | 5 | OK
|  | User | Bill Page |  | 2023-04-11 | 2023-04-25 | 5 | OK
4 | Trần Thụ Huy | Admin | Film manager Page (View,New, Edit, Delete Film) | Film,Actor, FilmGenreDetails, ActorOfFilm | 2023-03-21 | 2023-03-25 | 5 | OK
[5 empty] | 2023-03-28 | 2023-04-01 | 5 | OK
|  |  | Export report for Film by Excel |  | 2023-04-04 | 2023-04-08 | 5 | OK
|  | User | Home Page for Admin and Employee |  | 2023-04-11 | 2023-04-25 | 5 | OK
Note: | 1. Table name is valid if data is changed from the table;
2. To be invalid if data is got from the table only.