## Tasksheet
No | Member | Contents |  | Table Name | Activity Plan | Date of Preparation of Activity Plan
[5 empty] | Planed Start Date | Actual Start Date | Actual Days | Status
1 | Lê Viết Đông | Admin | Form for input: Room,RoomType,SeatType | Ticket, Room,RoomType, SeatType,RoomSeatDetails | 2023-03-21 | 2023-03-21 | 5 | OK
[5 empty] | 2023-03-21 | 2023-03-21 | 5 | OK
|  | User | Manage Ticket, and order product and export report by Excel |  | 2023-03-21 | 2023-03-21 | 5 | OK
|  |  | note: Ticket table is empty and insert auto when choose Ticket on user interface |  | 2023-03-21 | 2023-03-21 | 5 | OK
[5 empty] | 2023-03-21 | 2023-03-21
2 | Huỳnh Tấn Phước | Admin | Form for input: Employee | Employee, WorkingSession, | 2023-03-21 | 2023-03-21 | 5 | OK
[5 empty] | 2023-03-21 | 2023-03-21 | 5 | OK
[5 empty] | 2023-03-21 | 2023-03-21 | 5 | OK
|  | User | Manage login process Manage Personal Account Manage working session and export report by Excel |  | 2023-03-21 | 2023-03-21 | 5 | OK
[5 empty] | 2023-03-21 | 2023-03-21
3 | Nguyễn Nhật Minh | Admin | Form for input: Customer | Customer, Bill | 2023-03-21 | 2023-03-21 | 5 | OK
[5 empty] | 2023-03-21 | 2023-03-21 | 5 | OK
|  | User | Manage Bill and export Bill |  | 2023-03-21 | 2023-03-21 | 5 | OK
[5 empty] | 2023-03-21 | 2023-03-21 | 5 | OK
[5 empty] | 2023-03-21 | 2023-03-21
4 | Trần Thụ Huy | Admin | Form for input: Film, Schedule,Actor | Film,Actor, Schedule, TimeDetails | 2023-03-21 | 2023-03-21 | 5 | OK
[5 empty] | 2023-03-21 | 2023-03-21 | 5 | OK
|  | User | Export report for Film by Excel |  | 2023-03-21 | 2023-03-21 | 5 | OK
[5 empty] | 2023-03-21 | 2023-03-21 | 5 | OK
Note: | 1. Table name is valid if data is changed from the table;
2. To be invalid if data is got from the table only.